## Summary
Audio Sentinel - Master Task Tracker
Project overview | Value | Owner | Total tasks | Completed
Total tasks | 72 | Person A | 68 | 68
Completed | 72 | Person B | 4 | 4
In progress | 0
Not started | 0
Current next task | All planned tasks complete

## Task Register
Audio Sentinel - Editable Task Register
Person A covers all remaining A and B tasks while Person B is unavailable. Keep task IDs and verify dependencies before continuing.
Phase | Task ID | Task | Owner | Status | Dependencies / Notes
Dataset Intake | D0.1 | Identify candidate acoustic datasets | Person A | Complete | Completed dataset phase
Dataset Intake | D0.2 | Review dataset licenses, relevance, and label mappings | Person B | Complete | Completed dataset phase
Dataset Intake | D0.3 | Download approved datasets into data/raw/ | Person A | Complete | Completed dataset phase
Dataset Intake | D0.4 | Record dataset sources and intake metadata | Person B | Complete | Completed dataset phase
Foundation | A0.1 | Define v1 event labels, risk levels, consent boundaries, and JSON schemas | Person A | Complete
Foundation | B0.1 | Set up package test structure, developer tooling, and shared test fixtures | Person B | Complete
Foundation | A0.2 | Create central configuration models and directory/path helpers | Person A | Complete | Depends on A0.1
Foundation | B0.2 | Add configuration-validation tests and project health checks | Person B | Complete | Depends on A0.2
Foundation | A0.3 | Define module interfaces for preprocessing through alerts | Person A | Complete | Depends on A0.1
Audio Preparation | A1.1 | Define preprocessing settings and prepared-audio manifest schema | Person A | Complete | Depends on A0.2
Audio Preparation | B1.1 | Implement local audio loading and input validation | Person A | Complete | Depends on A1.1
Audio Preparation | A1.2 | Implement mono conversion, resampling, and loudness normalization | Person A | Complete | Depends on A1.1
Audio Preparation | B1.2 | Implement optional configurable noise-reduction module | Person A | Complete | Depends on A1.1
Audio Preparation | B1.3 | Implement deterministic overlapping window segmentation | Person A | Complete | Depends on A1.1
Audio Preparation | A1.3 | Implement prepared-output persistence and manifests | Person A | Complete | Depends on A1.2 and B1.3
Audio Preparation | A1.4 | Integrate preparation steps into one pipeline service | Person A | Complete | Depends on B1.1, B1.2, A1.3
Audio Preparation | B1.4 | Add unit tests for loader, noise reduction, and segmentation | Person A | Complete | Depends on B1.1, B1.2, B1.3
Audio Preparation | A1.5 | Add preparation integration tests and sample-clip smoke test | Person A | Complete | Depends on A1.4
Log-Mel Features | A2.1 | Define Log-Mel feature contract and metadata schema | Person A | Complete | Depends on A1.5
Log-Mel Features | B2.1 | Implement Log-Mel spectrogram generation | Person A | Complete | Depends on A2.1
Log-Mel Features | A2.2 | Implement feature storage and source-window linkage | Person A | Complete | Depends on A2.1
Log-Mel Features | B2.2 | Add feature shape, range, and determinism tests | Person A | Complete | Depends on B2.1
Log-Mel Features | A2.3 | Integrate feature extraction with preparation pipeline | Person A | Complete | Depends on B2.1 and A2.2
Acoustic Detection | A3.1 | Choose pretrained acoustic model and define label mapping | Person A | Complete | Depends on A2.3
Acoustic Detection | B3.1 | Implement isolated acoustic-model loader with version metadata | Person A | Complete | Depends on A3.1
Acoustic Detection | A3.2 | Implement inference orchestration over windows/features | Person A | Complete | Depends on B3.1
Acoustic Detection | B3.2 | Implement event aggregation across overlapping windows | Person A | Complete | Depends on A3.1
Acoustic Detection | A3.3 | Produce timestamped acoustic-evidence JSON | Person A | Complete | Depends on A3.2 and B3.2
Acoustic Detection | B3.3 | Add acoustic loader and aggregation unit tests | Person A | Complete | Depends on B3.1 and B3.2
Acoustic Detection | A3.4 | Evaluate acoustic detection against labeled samples | Person A | Complete | Depends on A3.3
Speech and Transcription | A4.1 | Define speech-evidence schema and reliability rules | Person A | Complete | Depends on A1.5
Speech and Transcription | B4.1 | Implement pretrained voice-activity-detection wrapper | Person A | Complete | Depends on A4.1
Speech and Transcription | A4.2 | Implement speech-segment extraction and timestamp handling | Person A | Complete | Depends on B4.1
Speech and Transcription | B4.2 | Implement offline transcription-model wrapper | Person A | Complete | Depends on A4.1
Speech and Transcription | A4.3 | Orchestrate transcription and low-confidence handling | Person A | Complete | Depends on A4.2 and B4.2
Speech and Transcription | B4.3 | Add VAD and transcription wrapper tests | Person A | Complete | Depends on B4.1 and B4.2
Speech and Transcription | A4.4 | Add speech-branch integration tests | Person A | Complete | Depends on A4.3
Language Understanding | A5.1 | Define language categories, reason codes, and evidence schema | Person A | Complete | Depends on A4.4
Language Understanding | B5.1 | Create versioned keyword, phrase, and negation rule data | Person A | Complete | Depends on A5.1
Language Understanding | A5.2 | Implement transcript-analysis engine | Person A | Complete | Depends on A5.1 and B5.1
Language Understanding | B5.2 | Create labeled language fixtures including harmless negations | Person A | Complete | Depends on A5.1
Language Understanding | A5.3 | Add language-analysis tests and false-positive safeguards | Person A | Complete | Depends on A5.2 and B5.2
Risk Assessment | A6.1 | Define risk inputs, 0-100 score, severity bands, and missing-data policy | Person A | Complete | Depends on A3.4, A4.4, A5.3
Risk Assessment | B6.1 | Implement configurable risk-scoring rules engine | Person A | Complete | Depends on A6.1
Risk Assessment | A6.2 | Integrate acoustic, speech, and language evidence into risk inputs | Person A | Complete | Depends on A6.1
Risk Assessment | B6.2 | Create risk-scoring tests for normal and edge scenarios | Person A | Complete | Depends on A6.1
Risk Assessment | A6.3 | Add a trainable risk-model interface for future custom training | Person A | Complete | Depends on A6.1
Risk Assessment | A6.4 | Validate risk-score behavior and thresholds | Person A | Complete | Depends on B6.1, A6.2, B6.2
Verification and Consensus | A7.1 | Define consensus policy and outcomes: no action, log, review, alert | Person A | Complete | Depends on A6.4
Verification and Consensus | B7.1 | Implement evidence-agreement and conflict-detection rules | Person A | Complete | Depends on A7.1
Verification and Consensus | A7.2 | Implement final verification decision service | Person A | Complete | Depends on A7.1 and B7.1
Verification and Consensus | B7.2 | Add disagreement, low-confidence, and false-alert safety tests | Person A | Complete | Depends on B7.1
Verification and Consensus | A7.3 | Add custom verification-model interface for future training | Person A | Complete | Depends on A7.1
Verification and Consensus | A7.4 | Validate consensus outcomes on end-to-end scenarios | Person A | Complete | Depends on A7.2 and B7.2
Offline Evaluator and Alerts | A8.1 | Build end-to-end evaluator orchestration for one recorded clip | Person A | Complete | Depends on A7.4
Offline Evaluator and Alerts | B8.1 | Implement versioned final JSON report serialization | Person A | Complete | Depends on A7.1
Offline Evaluator and Alerts | A8.2 | Implement local alert creation and audit records | Person A | Complete | Depends on A8.1 and B8.1
Offline Evaluator and Alerts | B8.2 | Implement CLI commands for evaluation and report inspection | Person A | Complete | Depends on A8.1 and B8.1
Offline Evaluator and Alerts | A8.3 | Implement local API endpoint and request validation | Person A | Complete | Depends on A8.1
Offline Evaluator and Alerts | B8.3 | Add CLI and report integration tests | Person A | Complete | Depends on B8.2
Offline Evaluator and Alerts | A8.4 | Add end-to-end API and evaluator tests | Person A | Complete | Depends on A8.2 and A8.3
Evaluation and Release | B9.1 | Build repeatable evaluation manifest and metric calculations | Person A | Complete | Depends on A8.4
Evaluation and Release | A9.1 | Run evaluation and document false-positive and false-negative findings | Person A | Complete | Depends on B9.1
Evaluation and Release | B9.2 | Implement retention/deletion settings and local audit-log tests | Person A | Complete | Depends on A8.2
Evaluation and Release | A9.2 | Document consent, authorized use, human review, and model limitations | Person A | Complete | Depends on A9.1
Evaluation and Release | A9.3 | Finalize offline MVP demonstration script | Person A | Complete | Depends on A9.2 and B9.2
Live Device Integration | A10.1 | Define authorized-device enrollment and streaming interface | Person A | Complete | Depends on A9.3
Live Device Integration | B10.1 | Implement streaming audio-ingestion client/service | Person A | Complete | Depends on A10.1
Live Device Integration | A10.2 | Adapt pipeline to rolling live windows | Person A | Complete | Depends on B10.1
Live Device Integration | B10.2 | Implement buffering, reconnect, and backpressure behavior | Person A | Complete | Depends on B10.1
Live Device Integration | A10.3 | Measure latency, reliability, and alert timing | Person A | Complete | Depends on A10.2 and B10.2
Live Device Integration | A10.4 | Conduct final privacy, security, and deployment review | Person A | Complete | Depends on A10.3

## Collaboration Guide
Collaboration Guide
Role | Working agreement
Person A | May create, edit, remove, test, and commit files for assigned tasks. Person A owns shared contracts and integration.
Person B | Currently unavailable. Person A covers all remaining Person B tasks; task IDs stay unchanged.
Integration gate | Run the completed task tests and relevant integration tests before starting dependent work.
Task handoff format | Task goal; files to add/edit/remove; exact code content; public interface; tests; verification commands; expected commit message.